## Project schedule
| Liugong Finance | [11 empty] | Date: | [7 empty] | 2025-12-22
| IT DEPT | [11 empty] | Display week: | [7 empty] | 6
[13 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02
| TASK | Department | ASSIGNED TO | Business SOP | PROGRESS | SYSTEM READINESS | LINKED CRs | DELIVERY | STATUS | START | END | time axis 2026-01-12 to 2026-03-08
 | time axis 2026-01-12 to 2026-03-08
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Application In | BS |  | 0% | 100% | 96% |  |  |  | 2025-12-22 | 2026-02-27 | 68
| 1. Select Relevent Products, Dealer Information |  | Bu Arianti, Pak Olly | 0% | 100% | 80% | - | - |  | 2025-12-22 | 2026-01-13 | 23
| 1. Input Applicant Information 2. Input Address, Reference, Project, shareholder information etc. |  | Bu Arianti, Pak Olly | 0% | 100% | 100% | LFIUAT001 - Proposoal enhancement | 06th Feb | Pass | 2025-12-22 | 2026-02-27 | 68
| 1. Input Facility Information |  | Bu Arianti, Pak Olly | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| 1. Submit application For Analysis |  | Bu Arianti, Pak Olly | 0% | 100% | 100% | Credit Line Management Enhancement | TBD |  | 2025-12-22 | 2026-01-13 | 23
| Stationary/Document/Reports |  | Bu Arianti, Pak Olly | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| CAFA | CA |  | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-02-27 | 68
| 1. Finacial Analaysis of Facility request |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| 1. AML, CFT Scoring & analysis | AML | Pak Pram | 0% | 100% | 100% | AML Enhancement (Transaction Monitoring) | 06th Feb | Pass | 2025-12-22 | 2026-02-27 | 68
| 1. Change Request process |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| 1. Dealer Recourse |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| Staionary/Document |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| Signing CLF | CA |  | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-02-27 | 68
| 1. Votting Process initiated 2. Votting process Completed |  | Bu Arianti, Pak Olly, Bu Ria & Credit Commetti | 0% | 100% | 100% | LFIUAT010 - Modification Voting Approval Screen | 06th Feb | Pass | 2025-12-22 | 2026-02-27 | 68
| 1. Facility Approval Request Approval 2. Conditional Approval |  | Bu Arianti, Pak Olly, Bu Ria & Credit Commetti | 0% | 100% | 100% | LFIUAT011 - Adjusment Voting Screen Details | 06th Feb | Pass | 2025-12-22 | 2026-02-27 | 68
| 5. Document/Stationary check |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| Document Printing | BS |  | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-02-27 | 68
| 1. Asset Application creation |  | Bu Arianti, Pak Olly, | 0% | 100% | 100% | LFIUAT003 - Application of Disbursement Mandatory Field Modification | 06th Feb | Pass | 2025-12-22 | 2026-01-13 | 23
| 1. Check Structure & non- structure plans 2. Check Multi assets in application |  | Bu Arianti, Pak Olly, | 0% | 100% | 100% | Club Asset | 06th Feb | Pass | 2025-12-22 | 2026-02-27 | 68
| 1. Check Repayment Plan Data 2. Check Insurance, Subsidy |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% | Structured Type - Principal % LFIUAT006 - Cross Default/Cross Collateral Function | 13th March TBD | In Development | 2025-12-22 | 2026-01-13 | 23
| 1. Submit asset application For Approval |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| 1. Convert application into Contract |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% | Calculation Simulation | 06th Feb | Pass | 2025-12-22 | 2026-01-13 | 23
| 1. Check Stationary/Documents |  | Bu Arianti, Pak Olly, Bu Ria | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| Disbursement | BS |  | 0% | 88.89% | 94.44% |  |  |  | 2025-12-22 | 2026-03-31 | 100
| 1. Check Financial data in Contract Actiation |  | Bu Arianti, Pak Olly, Bu Julia | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| 1. Input BAST, PJB data, Ceritifcate of Ownershipt etc… |  | Bu Arianti, Pak Olly, Bu Julia | 0% | 100% | 100% | LFIUAT004 - Contract Activation Enhancement | 06th Feb | Pass | 2025-12-22 | 2026-02-27 | 68
| 1. Check if Financial Modification is required |  | Bu Arianti, Pak Olly, Bu Julia | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-01-13 | 23
| 1. PDC Management | Accounting | Bu Arianti, Pak Olly, Pak Richard, Bu Julia | 0% | 50% | 100% | LFIUAT007 - PDC Auto Allocate Features | TBD |  | 2025-12-22 | 2026-01-13 | 23
| 1. Contract Go Live |  | Bu Arianti, Pak Olly, Pak Richard, Bu Julia | 0% | 100% | 100% | LFIUAT004 - Contract Activation Enhancement | 06th Feb | Pass | 2025-12-22 | 2026-01-13 | 23
| 1. Payable Generation |  | Bu Arianti, Pak Olly, Pak Richard, Bu Julia | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-02-27 | 68
| 1. Disbursement to Dealer | Accounting | Pak Richard | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-02-27 | 68
| 1. Accounting Generation | Accounting | Bu Julia | 0% | 60% | 60% | Journel | 13th March | In Development | 2026-02-27 | 2026-03-31 | 33
| Staionary/Document |  | Bu Arianti, Pak Olly, Bu Julia | 0% | 90% | 90% | LFI014 - Stationary Check | 13th March | In Development | 2026-02-27 | 2026-03-31 | 33
| Collection Process | QA |  | 0% | 75% | 87.5% |  |  |  | 2025-12-22 | 2026-04-30 | 130
| 1. Collection Followup request |  | Pak Isfar, Pak Dibya | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-04-30 | 130
| 2. Monitoring of Contract with overdue |  | Pak Isfar, Pak Dibya | 0% | 100% | 100% | AR Monitoring and Assignment | 06th Feb | Pass | 2025-12-22 | 2026-02-27 | 68
| 3. Followups |  | Pak Isfar, Pak Dibya | 0% | 100% | 100% |  |  |  | 2025-12-22 | 2026-04-30 | 130
| Staionary/Document |  | Pak Isfar, Pak Dibya | 0% | 0% | 50% |  |  |  | 2025-12-22 | 2026-04-30 | 130
| Payment Default Settlement | QA |  | 0% | 0% | 90% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Check contract status |  | Pak Isfar, Pak Dibya | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Check Restrcturing possiblity 2. Use Case Management to Record for Approval of Restructuring |  | Pak Isfar, Pak Dibya | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. If Approved by BOD, Perform System Restructuring |  | Pak Isfar, Pak Dibya | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Check Restructuring Results |  | Pak Isfar, Pak Dibya | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| Staionary/Document |  | Pak Isfar, Pak Dibya | 0% | 0% | 50% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| Restrcuturing Process | QA |  | 0% | 0% | 75% |  |  |  | 2026-04-06 | 2026-05-29 | 54
| 1. Get Approval for Restructuring using Case Managenemt |  | Pak Isfar, Pak Dibya | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 2. Perform Restrcturing Approval |  | Pak Isfar, Pak Dibya | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 3. Stationary/Document |  | Pak Isfar, Pak Dibya | 0% | 0% | 50% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 4. Accounting Generation | Accounting | Bu Julia | 0% | 0% | 50% | Journel |  |  | 2026-04-06 | 2026-05-29
| Reposession | BS |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Initiate Reposession Request |  | Bu Arianti, Pak Olly | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 2. Redemption Expiry |  | Bu Arianti, Pak Olly | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 3. Asset Register |  | Bu Arianti, Pak Olly | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 4. Available for Remakreting |  | Bu Arianti, Pak Olly | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 5. Remarketing of Asset |  | Bu Arianti, Pak Olly | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| Inventory Asset Selling | QA |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Asset Appraisal |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 2. Payment Receive |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| Recourse | QA |  | 0% | 0% | 87.5% |  |  |  | 2026-04-30 | 2026-05-29 | 30
| Recource BBG |  |  | 0% | 0% | 100% |  |  |  | 2026-04-30 | 2026-05-29 | 30
| Recource ALG |  |  | 0% | 0% | 100% |  |  |  | 2026-04-30 | 2026-05-29 | 30
| Recourse FPG |  |  | 0% | 0% | 100% |  |  |  | 2026-04-30 | 2026-05-29 | 30
| Staionary/Document |  |  | 0% | 0% | 50% | Waiting for Bi-Lingual Documents |  |  | 2026-04-30 | 2026-05-29 | 30
| BG |  |  | 0% | 0% | 87.5% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| BG Hold |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| BG Return |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| BG Re-Clearing |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30
| Staionary/Document |  |  | 0% | 0% | 50% | Waiting for Bi-Lingual Documents |  |  | 2026-04-06 | 2026-04-30 | 25
| Stop Engine |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Stop Engine |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
| Block Supply |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Block Supply |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
| Filling Document |  |  | 0% | 0% | 50% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1.Filling Document |  |  | 0% | 0% | 50% |  |  |  | 2026-04-06 | 2026-04-30 | 25
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
| Ownership Document Releasing |  |  | 0% | 0% | 83.33% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Article Closing request approval |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Refund/Treat as Income actions |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| Stationary/Documents |  |  | 0% | 0% | 50% | Waiting for Bi-Lingual Documents |  |  | 2026-04-06 | 2026-04-30 | 25
| Complaint Handling |  |  | 0% | 0% | 83.33% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Case management to log Customer complaint |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| 1. Case clousure with resolution |  |  | 0% | 0% | 100% |  |  |  | 2026-04-06 | 2026-04-30 | 25
| Stationary/Documents |  |  | 0% | 0% | 50% | Waiting for Bi-Lingual Documents |  |  | 2026-04-06 | 2026-04-30 | 25
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
|  |  |  | 0% | 0% | N/A |  |  |  | 2026-04-06
| Emoticons | QA |  | 0% | 0% | 50% |  |  |  | 2026-04-30 | 2026-05-29 | 30
| 1.Emoticons |  |  | 0% | 0% | 50% | No Requirement shared yet |  |  | 2026-04-30 | 2026-05-29 | 30
| Risk Control | AML |  | 0% | 41.67% | 80% |  |  |  | 2025-12-22 | 2026-06-30 | 191
| AI Empowerment and Efficiency | CA |  | 0% | 0% |  |  |  |  | 2026-04-30 | 2026-05-28 | 29
| AML Score |  |  | 0% | 25% | 60% | AML Scoring | 27th March | In development | 2026-04-24 | 2026-05-28 | 35
| Anti-Money Laundering Detection Rule Deployment |  |  | 0% | 100% | 100% | AML Enhancement | 06th Feb | Pass | 2025-12-22 | 2026-02-27 | 68
| Decision Engine | CA |  | 10% | 10% | 10% |  |  |  | 2026-06-15 | 2026-06-30 | 16
| Decision Engine Rules |  |  | 10% | 10% | 10% |  |  |  | 2026-06-15 | 2026-06-30 | 16
| CAP Application Enhancement |  |  | 10% | 10% | 10% |  |  |  | 2026-06-15 | 2026-06-30 | 16
Insert new rows ABOVE this one

## Overall planning
Phase | System Process flow | Start time | End time | Current Business SOP | Core System Readiness (NETSOL) | Production Business Case Exists | Status | Automation Target % | Automation Achievement % | UAT(new)&requirements |  |  | Process reengineering |  |  | Comment
[10 empty] | 1.Using real-case testing, gathering feedback on issues, and proposing actual needs 2.Stationary/Document/Reports | System debugging | Retest and go live | 1.Process improvement 2.Online transformation of offline processes 3.Disassembly process flow nodes and PIC 4.New Reports | System debugging | Retest and go live
From application in to payment receive | Application In | 2025-12-22 | 2026-02-27 | 100% | 96% | Yes | #REF! | 90% | 70% | 100% | 90% | 0% | 75% | 0% | 0% | OCR
| CAFA | 2025-12-22 | 2026-02-27 | 100% | 100% | Yes | #REF! | 70% | 50% | 100% | 100% | 0% | 70% | 0% | 0% | Onsite check, Manual Review, Decision Engine
| Signing CLF | 2025-12-22 | 2026-02-27 | 100% | 100% | Yes | #REF! | 80% | 60% | 100% | 100% | 0% | 80% | 0% | 0% | e-Sign
| Document Printing | 2025-12-22 | 2026-02-27 | 100% | 100% | Yes | #REF! | 95% | 90% | 100% | 95% | 0% | 60% | 0% | 0%
| Disbursement | 2025-12-22 | 2026-03-31 | 100% | 94.44% | Yes | #REF! | 90% | 70% | 100% | 69% | 0% | 70% | 0% | 0% | Bank integration
| Collection Process-payment receive | 2025-12-22 | 2026-03-31 | 100% | 87.5% | Yes | #REF! | 80% | 60% | 50% | 50% | 0% | 10% | 0% | 0% | Manual follow-up, Notification
| Accounting Generation | 2026-01-26 | 2026-03-31 | 100% | 60% | Yes | 60% | 95% | 60% | 30% | 30% | 0% | 30% | 0% | 0%
AI | AI | 2026-02-01 | 2026-05-31 | N/A |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Define MVP
QA and others Post-loan management | Payment Default Settlement | 2026-04-06 | 2026-04-30 | 100% | 90% | No | #REF! | 60% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | Legal and customer negotiation
| Restrcuturing Process | 2026-04-06 | 2026-04-30 | 100% | 75% | No | #REF! | 50% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | Manual process case by case
| Reposession | 2026-04-06 | 2026-04-30 | 100% | 100% | No | #REF! | 40% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | On-site execution
| Inventory Asset Selling | 2026-04-06 | 2026-04-30 | 100% | 100% | No | #REF! | 60% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | Manual process case by case
| Recourse | 2026-04-30 | 2026-05-29 | 100% | 87.5% | No | #REF! | 50% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | Manual and legal process case by case
| BG | 2026-04-06 | 2026-04-30 | 100% | 87.5% | Yes | #REF! | 70% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | Manual process
| Stop Engine | 2026-04-06 | 2026-04-30 | 100% | 100% | No | #REF! | 80% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | GPS Integration
| Block Supply | 2026-04-06 | 2026-04-30 | 100% | 100% | No | #REF! | 80% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | GPS Integration
| Filling Document | 2026-04-06 | 2026-04-30 | 100% | 50% | N/A | #REF! | 90% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
| Ownership Document Releasing | 2026-04-06 | 2026-04-30 | 100% | 83.33% | No | #REF! | 70% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | Manual process case by case
| Complaint Handling | 2026-04-06 | 2026-04-30 | 100% | 83.33% | No | #REF! | 60% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | Manual process case by case
| Emoticons | 2026-04-30 | 2026-05-29 | 100% | 50% | Yes | #REF! | 85% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | Parameter List
| Risk Control | 2026-04-24 | 2026-05-28 | 100% | 80% | Yes | #REF! | 65% | 20% | 50% | 17% | 0% | 0% | 0% | 0% | Manual Review
| Accounting Generation | 2025-12-22 | 2026-05-29 | 100% | 50% | Yes | #REF! | 95% | 60% | 0% | 0% | 0% | 0% | 0% | 0%
| Decision Engine | 2026-06-15 | 2026-06-30 | N/A | 10% | Yes | 10% | 95% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | Decision Engine
Phase | System Process flow | start time | End time |  |  |  | Status |  |  | Process reengineering |  |  | UAT(new)&requirements
[10 empty] | 1.Process design 2.requirements 3.Disassembly process flow nodes and PIC | System debugging | Retest and go live | 1.Using real-case testing, gathering feedback on issues, and proposing actual needs 2.Stationary/Document/Reports | System debugging | Retest and go live
System iteration upgrade and new feature development | Iteration - Payment Interface Bank-Enterprise Direct Link | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-支付接口银企直联
| Iteration - OCR Interface | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-OCR接口
| Iteration - Notification Interface | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-通知接口
| Iteration - GPS Interface | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-GPS接口
| Iteration - Data Warehouse Construction | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-数仓搭建（基础框架搭建、数据存储追踪） | (Basic Framework Construction, Data Storage Tracking)
| Iteration - SLIK & SILARAS Submission | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-SLIK&SILARAS报送
| Iteration - Manufacturer AR Management | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-厂家AR管理模块（含经销商、厂家界面优化） | (Including Dealer and Manufacturer Interface Optimization)
| Iteration - Joint Leasing Module | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-联合租赁模块
| Iteration - Channel Business Module | [5 empty] | #REF! |  |  | 0% | 0% | 0% | 0% | 0% | 0% |  | 项目-核心系统迭代-通道业务模块
Formulas:
End time = [End time, row above]
Note on P2: lu'xue: 流程改造 包括 流程提升 线下流程线上化 拆解流程流转节点及责任人